## READ ME FIRST
VER CINEMATIC CQBR — INPUT FORM
Fill every tab. Grayed rows show format — overwrite with real data.
Required tabs: 1. Engagement Header, 2. By The Numbers, 3. SLA Performance, 5. Milestones Delivered, 7. Improvement Areas, 9. Forward Commitments
Save as .xlsx before uploading to the Cinematic Generator.

## 1. Engagement Header
VER CINEMATIC CQBR — ENGAGEMENT HEADER
Complete every row. Required fields are marked with *.
FIELD | YOUR RESPONSE | NOTES
Vendor Name * | Infosys | Required — must match vendor registry name
Fiscal Year * | FY27 | e.g. FY27
Quarter * | Q1 FY27 | e.g. Q1 FY27
QBR Date | July 10, 2026 | Date of this review session
Vendor Lead | Priya Sharma | Primary vendor account lead
DET Sponsor | Casey Luciana Candelaria-Logan | DET primary relationship owner
Exec Sponsor | Roger Espinoza | Senior executive sponsor
Primary DET Pillar | Delivery Assurance & Operations | Primary DET business pillar
Service Lines Covered | Staff Augmentation, AppDev, AMS, QA | All service lines in scope
Total Headcount | 87 | Active billable headcount this quarter
Vendor Account Lead Name | Priya Sharma | Infosys account executive
Engagement Summary | Infosys delivered a stable Q1 FY27 with strong SLA adherence and zero P1 incidents. Knowledge transfer compliance remains the one open item — a formal improvement plan is in motion. VER rates the overall relationship as Healthy with one monitored risk. | 2-4 sentence strategic summary
Advisory Summary | Infosys delivered a stable Q1 FY27 with strong SLA adherence and zero P1 incidents. Knowledge transfer compliance remains the one open item — a formal improvement plan is in motion. VER rates the overall relationship as Healthy with one monitored risk. | VER narrative for Frame scene
Benchmark Notes | Infosys blended rate is 4.2% below DET preferred supplier benchmark for contingent workforce. Staff augmentation rates are competitive; application development rates warrant renegotiation at the Q3 FY27 renewal. | For Rate & Benchmark scene
SLA Summary | 5 of 6 SLAs met or exceeded target this quarter. Knowledge Transfer compliance is the sole open item at 87% vs 90% target — remediation plan submitted and accepted by DET. | Used in Quarter at a Glance scene
Attrition Summary | Overall attrition at 9.5% — below the 12% watch threshold. Staff Augmentation is the only elevated line at 11%; backfill pipeline is strong with no critical open roles. | Used in Relationship Health scene
Prior Quarter Score | 8.1 / 10 | VER composite score from last quarter

## 2. By The Numbers
VER CINEMATIC CQBR — BY THE NUMBERS
Up to 6 metrics. These become the full-screen animated 'By the Numbers' scene.
METRIC NAME | VALUE | CONTEXT (1 line) | TREND | COLOR
|  |  | Positive / Watch / Down | teal / green / amber / red / blue
Active Resources | 87 | Q1 FY27 — up 3 from Q4 FY26 | Positive | blue
SLA Compliance | 94.7% | 5 of 6 SLAs at or above target | Watch | amber
P1 Incidents | 0 | Zero critical incidents — third consecutive quarter | Positive | teal
Automated Test Cases | 340 | New regression cases — 18% release cycle reduction | Positive | green
On-Time Delivery | 96% | All milestones — up from 92% last quarter | Positive | teal
Open Action Items | 3 | Down from 7 — 4 closed this quarter | Positive | green

## 3. SLA Performance
VER CINEMATIC CQBR — SLA PERFORMANCE
List every contractual SLA. VER will flag any missing from contract.
SLA NAME | TARGET | ACTUAL | STATUS | NOTES
Green / Amber / Red
Incident Response Time | ≤ 4 hours | 3.2 hours avg | Green | Consistently meeting target — best quarter since engagement start
Knowledge Transfer Compliance | ≥ 90% | 87% | Amber | Third consecutive near-miss — formal improvement plan submitted and accepted
Release Defect Rate | ≤ 3% | 1.8% | Green | Below target — strong QA practice driven by Raj Kumar's automation work
Change Request Turnaround | ≤ 5 days | 4.1 days avg | Green | Improved from 5.8 days in Q4 — process change effective
Resource Backfill SLA | ≤ 30 days | 22 days avg | Green | Backfill velocity strong — all roles except QA filled on time
Executive Reporting On-Time | 100% | 100% | Green | All status reports delivered on schedule — automated pipeline live

## 4. Attrition
VER CINEMATIC CQBR — ATTRITION WATCH
Break down attrition by service line. VER uses this for risk scoring.
SERVICE LINE | ATTRITION % | ROLES AFFECTED | BACKFILL STATUS | REMEDIATION PLAN
Staff Augmentation | 11% | 9 roles | 7 of 9 backfilled | Backfill pipeline strong — 2 remaining roles interviewing; no critical gap
Application Development | 8% | 3 roles | 3 of 3 backfilled | Fully covered — no action required
QA Practice | 7% | 2 roles | 1 backfilled / 1 open | Open QA engineer role — shortlist submitted; target close by 2026-07-15
Managed Services | 6% | 1 role | 1 of 1 backfilled | Resolved this quarter — no ongoing risk

## 5. Milestones Delivered
VER CINEMATIC CQBR — MILESTONES DELIVERED
List all milestones committed to last quarter. VER cross-checks against prior commitments.
MILESTONE NAME | STATUS | DESCRIPTION (1-2 sentences) | SERVICE LINE
Delivered / Delayed / At Risk
ADAMS Q1 Stabilization | Delivered | Delivered on schedule with zero production incidents throughout the quarter. Longest incident-free run since engagement began. | Engineering
AMS Automation Phase 1 | Delivered | 340 manual regression cases automated — 18% release cycle reduction validated by DET QA team. | AMS
QA Framework Expansion | Delivered | Reusable test framework rolled out to two additional workstreams — ADAMS and AMS both onboarded. | QA Practice
Knowledge Transfer Plan v2 | Delayed | Submitted 5 days late due to mid-quarter resource change — accepted by DET with formal remediation timeline. | Engineering
AI Code Review POC | Delivered | 22% defect reduction observed in pilot sprint — approved for expanded Q2 pilot across 3 workstreams. | Innovation
Executive Reporting Automation | Delivered | Weekly status report automation live — reduces manual prep time by 3 hours per week starting Q2. | Operations

## 6. Innovation
VER CINEMATIC CQBR — INNOVATION & CAPABILITY
Highlights vendor-led improvements, tooling, or process innovation.
INNOVATION NAME | DESCRIPTION | STATUS | MEASURABLE EVIDENCE
Piloting / Deployed / Planned
AI-Assisted Code Review | LLM-based code review POC integrated into ADAMS CI pipeline — catches defects before human review stage. | Piloting | 22% defect reduction in pilot sprint; approved for Q2 expansion to 3 workstreams
Regression Automation Framework | Reusable Selenium/pytest framework enables rapid test case authoring across all workstreams. | Deployed | 340 test cases automated; 18% release cycle reduction validated
NLP Knowledge Base Generator | Uses LLM to auto-generate internal knowledge articles from closed incident tickets — reduces KB authoring time. | Planned | Q2 FY27 pilot scheduled — target 50% reduction in KB authoring effort
AIOps Predictive Monitoring | ML-based alerting prototype for ADAMS — identifies anomaly patterns 4-6 hours before incident threshold breach. | Piloting | 3 incidents pre-empted in Q1 testing; estimated $24K/quarter SLA savings

## 7. Improvement Areas
VER CINEMATIC CQBR — IMPROVEMENT AREAS
Vendor fills what they know. VER supplements from DET stakeholder interviews.
ISSUE NAME | SEVERITY | DESCRIPTION | REMEDIATION PLAN | OWNER | TARGET DUE DATE
High / Medium / Low
Knowledge Transfer SLA | Medium | Score at 87% vs 90% contractual target for the second consecutive quarter — formal watch status. | Submit structured improvement plan with weekly milestones and measurement criteria by Q2 kickoff. | Priya Sharma | 2026-07-31
QA Engineer Backfill Gap | High | One QA engineer role open for 6+ weeks — creating risk to Q2 release cadence and regression coverage. | Resume shortlist submitted to DET HR; VER tracking weekly until role is filled. | Priya Sharma | 2026-07-15
Exec Reporting Latency | Low | Q4 FY26 monthly report delivered 2 days late — root cause was manual compilation process. | Executive reporting automation deployed this quarter — root cause fully resolved. | Raj Kumar | 2026-07-01

## 8. Team Recognition
VER CINEMATIC CQBR — TEAM RECOGNITION
Up to 4 people. DET validates nominations before they appear in the CQBR.
FULL NAME | ROLE / TITLE | DET IMPACT (2-3 sentences)
Ananya Patel | Senior Developer — ADAMS | Led ADAMS Q1 stabilization effort resulting in zero production incidents for 60 consecutive days — longest streak since engagement began. Mentored two junior developers who are now independently contributing to the QA automation framework.
Raj Kumar | QA Lead — Automation | Personally designed and delivered 340 automated regression test cases, cutting release cycle time by 18%. Built a reusable framework now adopted across two additional workstreams — recognized by DET architecture team as a best-practice implementation.
Deepa Nair | Delivery Manager | Managed a smooth resource transition during mid-quarter attrition without any SLA impact — zero missed commitments during the transition period. Proactively flagged the knowledge transfer risk to VER before it escalated to formal review.
Vikram Mehta | AIOps Engineer — Innovation | Designed and delivered the AIOps predictive monitoring POC that pre-empted 3 incidents in Q1 testing. Estimated $24K/quarter in SLA savings. Recognized by DET architecture lead as the most impactful innovation submission this quarter.

## 9. Forward Commitments
VER CINEMATIC CQBR — FORWARD COMMITMENTS
These become the published commitments tracked by VER for next quarter.
COMMITMENT | OWNER | DETAIL / SUCCESS CRITERIA | DUE DATE | CONSEQUENCE IF MISSED
Vendor / VER / Joint
Fill QA Engineer backfill role | Priya Sharma — Infosys | Place 1 qualified QA engineer from shortlist already submitted; DET interview scheduled for 2026-07-08. | 2026-07-15 | SLA breach risk in QA practice — formal escalation to contract review
Submit Knowledge Transfer improvement plan | Priya Sharma — Infosys | Formal written plan with weekly milestones, measurement criteria, and recovery timeline to 90% target. | 2026-07-31 | Formal escalation to vendor scorecard review and contract amendment discussion
Expand AI Code Review pilot to 3 workstreams | Vikram Mehta — Infosys | Extend AI code review POC to ADAMS, AMS, and QA teams — target 30% defect reduction at scale by Q2 close. | 2026-08-15 | Innovation credit forfeited on Q2 VER vendor scorecard
VER: Rate benchmark analysis for AppDev roles | VER — Casey Candelaria | Produce blended rate comparison against 3 preferred suppliers to inform Q3 FY27 renewal negotiation mandate. | 2026-08-01 | Renewal negotiation begins without rate leverage — estimated $1.2M exposure

## 10. Additional Context
VER CINEMATIC CQBR — ADDITIONAL CONTEXT
Anything that doesn't fit the structured tabs above. VER may use this in the Advisory Frame or Verdict scenes.
TOPIC | YOUR RESPONSE
Business Context | Infosys supports ADAMS (production stabilization), AMS (automation), Staff Augmentation, and QA across 4 DET pillars. Engagement is in year 2 of a 3-year contract with a renewal decision point in Q3 FY27.
Changes to Engagement | No scope changes this quarter. Mid-quarter resource realignment completed without SLA impact. AI practice formally added to SOW scope effective Q2 FY27.
Upcoming Renewal | Master contract renews Q3 FY27. VER will initiate rate renegotiation based on benchmark analysis — targeting 5-8% blended rate reduction with a 2-year term extension.
Relationship Assessment | Relationship rated Healthy overall. One monitored risk (Knowledge Transfer SLA). Delivery confidence is high. Infosys leadership engaged and responsive to all VER feedback this quarter.
Competitive Context | Two alternative vendors evaluated in Q4 FY26 benchmarking — Infosys remains price-competitive and quality-competitive. No RFP trigger conditions met this quarter.